## General Description
Description | Components | Goals | Techs | Requirements
A system includes robots that can be used in warehouse to transport packages based on defined map, fully autonomous operation | - AGV Robots - Main server - Bluetooth Low Energy stations (beacons) - Charging stations | - Intergrated with MES to build fully auto factory from production plans to handling opeartions | - For building prototype: .NET, C++, Javascript - In official version: .NET, C++, Javascript | - AGV must be auto in finding path, avoiding collisions, finding charging station - System must ensure speed of transporting of robots associated with efficiency in moving - Not having expensive hardwares but still be efficient

## Project Progress Tracking
Week | Task | Details | Estimated deadline | isComplete
09-14/01/2023 | AGV Project Description | - Make general workflow - Make software design diagram - Measure BLE signal strength and according receiving distance - Calculate basic positioning method base on BLE signal and laser data | 14/01 | 80%
16-21/01/2023 | AGV Codebase AGV Project Description AGV Documents | - Main Server Backend - Main Server Frontend - Robot Bash Script - Robot Console App - ESP32 firmware - Beacon firmware - Complete positioning method using beacon & laser sensor - Start writing document - Build hardware prototype | 31/01

## BLE in positioning
Beacon
Robot
Beacon Cover Range
QR Code/NFID Tag - Used to mark moving space/ Indicate package locations
Beacon signal is used for robot's alignment in running (only available on bluetooth 5.2++ which some popular ESP32 versions hasnt supported) - This part temporily is not applied in our project
Calculate Angle of Arrival between robot axis and beacon, then turn robot by the angle
Beacon signal strength measured by cover range radius (Based on basic measurements in good environment conditions)
30cm: -70 -> -60 dbm
3m: -80 -> -70 dbm
6m : -90 -> - 80dbm
Blank square: Where the package is put/Moving space
QR Code/RFID Tag can be removed if algo is good enough to determine position and path

## BLE Stations Installing Map
Package location
QR Code/ RFID Tag
Beacon
Robot
Beacon Cover Range

## BLE GATT
Beacon Name | UUID
| Service | Characteristics | Default Broadcasted Message
Beacon-1 | df8b3daf-6383-4b5e-9d18-23e7d042843d | c11a9227-4f05-49ea-b0dc-3913507bf42a | Beacon-1 Message
Beacon-2 | c8867ddf-e16e-406c-bf84-7c73c72ec855 | f4a46f10-d849-47d1-9738-ba3bdd7a461f | Beacon-2 Message
Beacon-3 | 3de4e477-75c1-4c72-88cb-f609a2cab2b3 | 4710acb1-ab86-4ea2-aea1-84237e7e130c | Beacon-3 Message
Beacon-4 | cd932085-9286-4138-9cd9-9956707e3f65 | 41ab2626-7129-44c2-ac20-3069737ec350 | Beacon-4 Message
Beacon-5 | b7078b93-019f-4000-be73-93b852dbdcba | 79d66fc5-0af3-47fe-b0b1-4b7759063615 | Beacon-5 Message
Beacon-6 | 858daf11-7d33-4f5c-b8b5-36c81841f7ae | d174dab1-829c-4cf8-b9b2-91c59ebea00e | Beacon-6 Message

## BOM(Cost Estimation)
Beacon Positioning Method (Estimated) |  |  |  |  | Line-Following Method (Estimated)
Components | Pricing |  | Deployment | Operation | Components | Pricing |  | Deployment | Operation
| VND | USD | Required power supply for plugging beacon | Heavily relies on algorithms to calibrate robot |  | VND | USD | Required sticking manually magnetic tape on the floor | Heavily relies on hardware & magnetic tape
Beacon/BLE Station (ESP32 module) Min required: Based on warehouse area | ~85.000 - 180.000 | ~3.5 - 8$ |  |  | Magnetic tape Min required: Based on warehouse area | ~40.000/50m | ~2$/50m
Laser Sensor (for distance detection) Min required: >= 8pcs/robot | 50.000 - 500.000 | ~2$ - 25$ |  |  | Magnetic sensor Min required: >=1 piece/robot | > 5.000.000 | > 250$
RFID Reader (Optional) |  |  |  |  | RFID Reader (Optional)

## Workflows
General
AGV

## Dashboard UI Designs
Main Server - Dashboard Homepage